## Sheet1
LGD Batch Implementation Activities & Timelines
| ACTIVITY | Specific Tasks | Timetimes
i. | Design | - Implementation plan | 2020-07-07
|  | - System Architecture design | 2020-07-07
|  | - Model execution process flow | 2020-07-07
|  | - Model Flow Diagram | 2020-07-07
|  | - Data flow diagram | 2020-07-07
|  | - Business Requirements document | 2020-07-20
ii. | ETL Data Validation Data Quality | - Extract EMDW Data & other sources | 2020-07-07
|  | - Extract and prepare mapping tables | 2020-07-07
|  | - Applying all necessary transformation | 2020-07-07
|  | - compare data with approved model's documentation | 2020-07-07
|  | - Check corrupt and missing data, | 2020-07-07
|  | - Gap analysis | 2020-08-07
|  | - Data validation, Integrity & Accuracy | 2020-08-07
|  | - Model ready data and Load data | 2020-08-20
iii. | Build | - The implementation models derived from the Model document | 2020-08-07
|  | - Code Models with Business Rules | 2020-08-07
|  | - Automation of the LGD process | 2020-09-20
iv. | Model testing | - Test coded models and business rules whether they meet approved model specifications | 2020-09-20
|  | - Compare approved model scope with implementation | 2020-09-20

## Sheet2
Timothy | 1.2 | 45
Takra | 1.7 | 98